## Gantt Chart Template
GANTT CHART TEMPLATE | [17 empty] | https://goo.gl/PlIwL0
| PROJECT TITLE | Aplikasi Pengelolaan Pengajuan Pembuatan Surat pada Ur Admin
| PROJECT MANAGER | Evaliata Br. Sembiring
[7 empty] | Februari |  |  |  |  | March | [19 empty] | April | [19 empty] | June | [19 empty] | Juli
WBS NUMBER | BACKLOG/TASK TITLE | ASSIGNEES | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 3
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Project Conception and Initiation
1.1 | Briefing project, pembagian kelompok. | Adhyca H | 24/2/2025 | 26/2/2025 | 3 | 100% | bar: WEEK 4 M to WEEK 4 W
1.1.1 | Penyusunan rencana kerja (rpp) dan pembagian kerja (work breakdown) |  | 27/2/2025 | 2025-07-03 | 6 | 70% | bar: WEEK 4 R to WEEK 1 F
1.2 | Presentasi rencana kerja |  |  |  |  | 0%
1.3 | Identifikasi kebutuhan pengguna |  |  |  |  | 0%
1.4 | Proses bisnis pengajuan surat |  |  |  |  | 0%
1.5 | Penyusunan spesifikasi kebutuhan sistem |  |  |  |  | 0%
1.6 | Arsitektur sistem |  |  |  |  | 0%
2 | Design
2.1 | Diskusi konsep desain aplikasi, identifikasi aktor, teknik eksekusi, framework |  |  |  |  | 0%
2.2 | Kebutuhan Fungsional dan non fungsional |  |  |  |  | 0%
2.3 | Rancangan: ERD flowchart |  |  |  |  | 0%
2.4 | Review validasi design sistem |  |  |  |  | 0%
3 | Implementation
3.1 | Implementasi front end dan back end, Troubleshooting |  |  |  |  | 0%
3.2 | Pengembangan front end |  |  |  |  | 0%
3.2.1 | Pengembangan back end |  |  |  |  | 0%
3.2.2 | Pengembangan fitur pengajuan surat |  |  |  |  | 0%
3.3 | Pengembangan fitur persetujuan |  |  |  |  | 0%
3.3.1 | Pengembangan fitur notifikasi dan manajemen pengguna |  |  |  |  | 0%
4 | Operate
4.1 | Menyusun skenario pengujian PL |  |  |  |  | 0%
4.2 | Pengujian PL |  |  |  |  | 0%
4.3 | Penyusunan Laporan dan luaran akhir PBL |  |  |  |  | 0%
4.4 | [5 empty] | 0%
5 | Pelaporan dan Presentasi
5.1 | Penyusunan Laporan tengah semester |  |  |  |  | 0%
5.2 | Presentasi progres PBL tengah semester |  |  |  |  | 0%
5.3 | Penyusunan Laporan dan luaran akhir PBL |  |  |  |  | 0%
5.4 | Pengumpulan luaran dan presentasi akhir |  |  |  |  | 0%
Note on C9: supar{dian}to -: Stage / Phase
Note on C10: supar{dian}to -: Backlog/Task